Church Event Planning Checklist

From “we should do something this fall” to tear-down — nothing forgotten.

Event overview

| Event |  | Date & time |  |
| --- | --- | --- | --- |
| Location |  | Point person |  |
| Expected attendance |  | Budget |  |
| The win |  |  |  |

8+ weeks out

☐  Define the purpose and the win (what does success look like?)

☐  Pick the date — check the church calendar AND school/community calendars

☐  Reserve rooms / lawn / gym with facilities

☐  Draft the budget and get it approved

☐  Recruit a core team: food, setup, kids, tech, promo

6 weeks out

☐  Plan promotion: announcements, social posts, flyer, church app

☐  Open sign-ups (headcount drives food + seating)

☐  Book any vendors, rentals, or guest speakers

☐  Decide the childcare plan

4 weeks out

☐  Recruit day-of volunteers (setup, check-in, food, tear-down)

☐  Order supplies and non-perishables

☐  First promo push from stage

2 weeks out

☐  Confirm every vendor and volunteer personally

☐  Print signage and check-in lists

☐  Draft the day-of run sheet (below)

☐  Second promo push + personal invites

Week of

☐  Final headcount → confirm food quantities

☐  Buy perishables

☐  Tech check: sound, mics, extension cords

☐  Brief volunteers: where, when, who's their lead

Day of

☐  Setup crew arrives (2+ hrs early)

☐  Check-in table staffed 30 min before start

☐  Someone is taking photos (for next year's promo!)

☐  Tear-down crew + building reset

After

☐  Thank-you texts to every volunteer within 48 hrs

☐  Reconcile expenses vs. budget

☐  Debrief with the core team: repeat / change / drop

☐  Follow up with every newcomer who signed in

Day-of run sheet

| Time | What | Who |
| --- | --- | --- |

Team

| Role | Name | Phone |
| --- | --- | --- |
| Point person |  |  |
| Setup lead |  |  |
| Food lead |  |  |
| Check-in |  |  |
| Kids / games |  |  |
| Tech / sound |  |  |
| Tear-down lead |  |  |