## Start Here
VBS Planning Template
A free template from MinistryPlanner.church
How to use this template:
1. Countdown Checklist tab — every task from six months out to the week after, with an owner, due date, and status dropdown. Done tasks turn green.
2. Budget tab — plan by category; the Remaining column turns red the moment a category goes over.
3. Volunteers tab — how many people each area needs vs. how many you have. The Gap column is your recruiting list.
4. Daily Schedule tab — the hour-by-hour run sheet your station leaders follow all week.
5. Supplies tab — one list, so twelve people don't each buy glue sticks.
Tip: recruit your crew leaders before you open registration. Kids capacity is set by volunteers, not by chairs.
Psst — everything in this spreadsheet (and the reminder texts, song keys, and lesson plans that go with it) happens automatically in MinistryPlanner. Free to try at ministryplanner.church.

## Countdown Checklist
Task | Owner | Due | Status | Notes
6+ months out
Pick VBS week + rain-backup week (check school & church calendars)
Choose theme / curriculum
Draft budget & get board approval
Recruit VBS director + area leads
4 months out
Order curriculum starter kit
Set registration cap (based on volunteer count!)
Open online registration
Start volunteer sign-ups + background checks
2 months out
Recruit crew leaders (1 per 5 kids)
Order t-shirts, decorations, craft supplies
Book sound/tech volunteers for rally times
Promo push: social, church announcements, yard signs
1 month out
Volunteer training night (safety, check-in, schedule)
Confirm snack plan + allergy protocol
Print rosters, name tags, crew lists
Decorating day sign-up
Week of
Decorate building (Saturday crew)
Tech run-through: rally videos, mics, slides
Stage check-in stations + signage
Daily 8:15 AM volunteer huddle
After
Follow-up postcards / emails to families
Thank-you notes to every volunteer
Debrief: what to repeat, what to change (write it down!)
Reconcile budget vs. actual

## Budget
Category | Budgeted | Actual | Remaining | Notes
Curriculum & media
Decorations
Crafts
Snacks
T-shirts
Promo & outreach
Facility & misc
Total

## Volunteers
Area | Needed | Have | Gap | Names / notes
Crew leaders | 10
Crew assistants (teens) | 10
Bible story station | 2
Games station | 3
Crafts station | 3
Snacks team | 4
Music / rally team | 3
Check-in desk | 3
Floaters / security | 2
First aid | 1

## Daily Schedule
Time | Len | Segment | Where | Who leads | Notes
8:15 | 15m | Volunteer huddle + prayer | Kids wing | Director | Coffee provided!
8:45 | 15m | Check-in opens | Lobby | Check-in team | Two lines: pre-reg + walk-up
9:00 | 20m | Opening rally (songs + theme skit) | Auditorium | Music team
9:20 | 25m | Rotation 1 | Stations | Crew leaders | Crews 1–2 Bible · 3–4 Games · 5–6 Crafts
9:45 | 25m | Rotation 2 | Stations | Crew leaders | Rotate clockwise
10:10 | 15m | Snack | Fellowship hall | Snacks team | Allergy table separate
10:25 | 25m | Rotation 3 | Stations | Crew leaders
10:50 | 20m | Closing rally + memory verse | Auditorium | Music team | Daily giveaway
11:10 | 20m | Pickup (match tag numbers!) | Lobby | Check-in team
11:30 | 20m | Reset stations for tomorrow | Stations | All leads

## Supplies
Item | Station | Qty needed | Who's getting it | Purchased?