## Start Here
VBS Planning Template
A free template from MinistryPlanner.church
How to use this template:
1. Countdown Checklist tab — every task from six months out to the week after, with an owner, due date, and status dropdown. Done tasks turn green.
2. Budget tab — plan by category; the Remaining column turns red the moment a category goes over.
3. Volunteers tab — how many people each area needs vs. how many you have. The Gap column is your recruiting list.
4. Daily Schedule tab — the hour-by-hour run sheet your station leaders follow all week.
5. Supplies tab — one list, so twelve people don't each buy glue sticks.
Tip: recruit your crew leaders before you open registration. Kids capacity is set by volunteers, not by chairs.
Psst — everything in this spreadsheet (and the reminder texts, song keys, and lesson plans that go with it) happens automatically in MinistryPlanner. Free to try at ministryplanner.church.

## Countdown Checklist
Task | Owner | Due | Status | Notes
6+ months out
Pick VBS week + rain-backup week (check school & church calendars) | Director | 2027-01-15 | Done
Choose theme / curriculum | Director | 2027-01-31 | In progress
Draft budget & get board approval | Director | 2027-02-15
Recruit VBS director + area leads | Pastor | 2027-02-28
4 months out
Order curriculum starter kit | Director | 2027-03-10
Set registration cap (based on volunteer count!) | Director | 2027-03-15
Open online registration | Comms | 2027-04-01
Start volunteer sign-ups + background checks | Kids lead | 2027-04-01
2 months out
Recruit crew leaders (1 per 5 kids) | Kids lead | 2027-05-01
Order t-shirts, decorations, craft supplies | Supplies lead | 2027-05-15
Book sound/tech volunteers for rally times | Tech lead | 2027-05-15
Promo push: social, church announcements, yard signs | Comms | 2027-05-20
1 month out
Volunteer training night (safety, check-in, schedule) | Director | 2027-06-08
Confirm snack plan + allergy protocol | Snacks lead | 2027-06-10
Print rosters, name tags, crew lists | Admin | 2027-06-20
Decorating day sign-up | Supplies lead | 2027-06-20
Week of
Decorate building (Saturday crew) | All hands | 2027-07-10
Tech run-through: rally videos, mics, slides | Tech lead | 2027-07-10
Stage check-in stations + signage | Admin | 2027-07-11
Daily 8:15 AM volunteer huddle | Director | 2027-07-12
After
Follow-up postcards / emails to families | Comms | 2027-07-20
Thank-you notes to every volunteer | Director | 2027-07-20
Debrief: what to repeat, what to change (write it down!) | Director | 2027-07-25
Reconcile budget vs. actual | Director | 2027-07-31

## Budget
Category | Budgeted | Actual | Remaining | Notes
Curriculum & media | 450 | 425
Decorations | 300 | 180
Crafts | 350 | 0
Snacks | 400 | 0
T-shirts | 600 | 640
Promo & outreach | 250 | 90
Facility & misc | 150 | 0
Total

## Volunteers
Area | Needed | Have | Gap | Names / notes
Crew leaders | 10 | 6 |  | Need 4 more — ask small groups
Crew assistants (teens) | 10 | 8
Bible story station | 2 | 2 |  | Karen F., James P.
Games station | 3 | 1 |  | Tom B.
Crafts station | 3 | 2
Snacks team | 4 | 2
Music / rally team | 3 | 3 |  | Sarah M. leading
Check-in desk | 3 | 2 |  | Lily T., Emily R.
Floaters / security | 2 | 1
First aid | 1 | 1 |  | Nurse Joan

## Daily Schedule
Time | Len | Segment | Where | Who leads | Notes
8:15 | 15m | Volunteer huddle + prayer | Kids wing | Director | Coffee provided!
8:45 | 15m | Check-in opens | Lobby | Check-in team | Two lines: pre-reg + walk-up
9:00 | 20m | Opening rally (songs + theme skit) | Auditorium | Music team
9:20 | 25m | Rotation 1 | Stations | Crew leaders | Crews 1–2 Bible · 3–4 Games · 5–6 Crafts
9:45 | 25m | Rotation 2 | Stations | Crew leaders | Rotate clockwise
10:10 | 15m | Snack | Fellowship hall | Snacks team | Allergy table separate
10:25 | 25m | Rotation 3 | Stations | Crew leaders
10:50 | 20m | Closing rally + memory verse | Auditorium | Music team | Daily giveaway
11:10 | 20m | Pickup (match tag numbers!) | Lobby | Check-in team
11:30 | 20m | Reset stations for tomorrow | Stations | All leads

## Supplies
Item | Station | Qty needed | Who's getting it | Purchased?
Craft kits (theme) | Crafts | 120 | Supplies lead | Done
Glue sticks | Crafts | 60 | Supplies lead | Done
Prize box items | Games | 150 | Tom B. | In progress
Goldfish + pretzels (nut-free) | Snacks | 15 boxes | Snacks lead | Not started
Juice boxes | Snacks | 300 | Snacks lead | Not started
Name tag rolls + lanyards | Check-in | 250 | Admin | Done
Butcher paper + paint (decor) | Decor | — | Supplies lead | In progress